## Problem Fix Determination
Sprint No. | Task | Description | Man Days (tentative) | Start Date | End Date | Milestones
1. Ontology, Taxonomy Structure Design
1 | Explore Existing Sources (SODA + HWSW) | Explore existing sources that can be used as a reference point for enhancing and populating ontologies. | 1 | 2018-05-21
1 | Define Taxonomy Structures | Define base taxonomy structure, by incorporating findings from existing sources. | 2 |  |  | Taxonomy Base structure
1 | Define Taxonomy Evolution Details | Define a process for enhancing and improving taxonomy. | 2 |  |  | Abstract for paper
1 | Formally Define and Populate Product Taxonomies | Finalize a taxonomy set and populate the selected products taxonomies | 5
1 | Define set of APARs and Products to work with | Select a set of APARs and products for populating the knowledge base. | 1
1 | Architecture Diagram | Generic Architecture Diagram for solution implementation | 1 |  | 2018-06-06 | Design Document including use cases, functional requirements, non functional requirements and architecture diagram -> logical, infrastructure and sequence diagrams
2. Data Curation and Transformations
2 | Feature Extraction | Extract features from the selected APARs text | 5 | 2018-06-07 |  | Identify and document features to be extracted within apars
2 | Natural Language Understanding | Design a process for context building. | 2
2 | Parse Tree Clusters | Parse tree cluster for extracting relationship from the text. | 5 |  |  | Parse tree clustering script
2 | Data Pipeline design | Define and integrate the components in the data flow pipeline. | 2 |  |  | Design for data ingestion pipeline
2 | Supporting DB design | Design a supporting DB structure to support our operations | 1 |  | 2018-06-26 | Metadata DB design structure
3. Identifying Entities and Relationships - I
3 | Entity Extraction design | Design an automated process for entity extraction. | 2 | 2018-06-27 |  | Entity Extraction Script
3 | Relationship extraction design | Design rule based process for relationship extraction. | 2 |  |  | Relationship extraction script
3 | Parse Tree Analysis | Analyze parse trees for additional insights | 3 |  |  | Insights from Parse Trees
3 | External Repositories Exploration (schema.org, wordnet etc) | Explore external repositories for enhancing the knowledge graph | 3 |  |  | Repostories feedback for synonyms etc
3 | Watson Knowledge Studio Exploration | Explore the Watson knowledge studio for value edition to process. | 3 |  | 2018-07-14 | WKS integration
4. Identifying Entities and Relationships - II
4 | Parsing Tickets | Design methods to process incoming tickets to extract knowledge context | 2 | 2018-07-15
4 | Ticket Search Algorithms and wrappers | Transform ticket context into cipher queries for fix identification | 1
4 | Process Design | Design the automated process for ticket processing and search for the system | 2
4 | Component Integration | Integrate individual knowledge graph components | 1
4 | Incorporate External Respositories | Enrich existing knowledge graph data with external repositories and links (HWSW, SODA, schema.org, wordnet) | 4
4 | Model Deployment | Deploy the models for entity and relationship extraction for incoming text and ticket ingestion | 1 |  | 2018-08-01
5. Dynamic Crawler Design
5 | Crawling Sources | Method to dynamically or manually identify sources to crawl | 1 | 2018-08-02
5 | Technology selection | Select technologies to build the crawler on | 1
5 | Crawler Implementation | Design a phase 1 basic crawler to crawler identified sources and feed the knowledge base | 5
5 | Crawler Support DB design | Design a db to store the crawler metadata | 2
5 | Crawler periodic reruns | Automate the crawler to recrawl and look for update or changes | 4 |  | 2018-08-19
6. Knowledge Graph Data Ingestion
6 | Dynamic Data Ingestion | Crawl fix and other related repositories and continuously ingest and grow the knowledge base | 4 | 2018-08-20
6 | Graph based search methods | Identify methods to accurately traverse the knowledge graph based on ticket or input context | 2
6 | Dynamic Structure Design for evolution | Identify how different data sources evolve and link up together as crawlers enhance knowledge base | 3
6 | Knowledge Base traversal methods | Explore methods to search and extract relevant information and identify cross account insights | 1 |  | 2018-09-04
7. Web Application Design
7 | Technology Selection | Select technologies to build an interface for the tool | 1 | 2018-09-05
7 | Interface Design | Build and select mockups to build the required application interface | 2
7 | Application Framework | Generate a baseline application framework on which the application will build on | 2
7 | Backend Integration | Integrate the application with the knowledge graph in an efficient way | 2
7 | Dashboarding and summary design | Build and select mockups for presenting application statistics on a simple dashboard | 2 |  | 2018-09-18
8. Querying Engine Interface
8 | Interface Implementation | Build out the application front end based on the mockups | 4 | 2018-09-19
8 | Dashboard Implementation | Build out the application dashboard based on the mockups | 4
8 | Recommendation Engine Design | Design a recommendation engine for searches in the knowledge graph for additional insights | 2
8 | Graph traversal based on relationships and entities |  | 2 |  | 2018-10-05
9. Functional, Integration, Stress Testing
9 | System Functional & Integration Testing | Carry out the functional and integration testing | 3 | 2018-10-06
9 | Regression Testing | Carry out regression testing | 3
9 | Performance Testing | Carry out performance and stress testing | 3
9 | Stress Testing | Determine maximum thresholds for application limits | 3 |  | 2018-10-22
10. User Acceptance Testing
10 | UAT Code Freeze | Freeze development activities | 1 | 2018-10-23
10 | User Acceptance Testing | Carry out UAT | 10
10 | Code Release | Release the developed code | 1 |  | 2018-11-10

## Sprint 1&2
| Task | Sub-Task | Status as of 31st May
Sprint 1 | Explore existing sources | Gain Access to exisiting sources | 100%
|  | Understand existing sources | 100%
| Taxonomy Structures | Discover and extract concepts | 70%. This is a running process that will continue to evolve throughout the project
|  | organize concepts | 70%. This is a running process that will continue to evolve throughout the project
|  | validate | 70%. This is a running process that will continue to evolve throughout the project
| Taxonomy Evolution | List methods for taxonomy evolution | deferred to a future sprint
|  | evaluate each method | deferred to a future sprint
| Populate Taxonomy | select product | deferred to a future sprint
|  | populate taxonomy | deferred to a future sprint
| Knowledge base | shortlist product and corresponding APAR | 100%
|  | Extract information for knowledge base | 100%
| Architecture Diagram | Discuss and agree on architecture | 100%
|  | draw architecture diagram | 75%. Delayed due to SoO deployment. Will not effect future sprints
| Sprint 5: Crawler Technology Selection |  | 100%
| Sprint 5: Crawler Implementation |  | 100%
| Sprint 3: Entity Extraction Design |  | 60%. Will be completed during sprint 3 as planned originally
| Sprint 3: Relationship Extaction Design |  | 60%. Will be completed during sprint 3 as planned originally
Sprint 2 | Data Extraction | design regex patterns
Scripts to remove un-needed text
Scripts to prepare data for context building
extract meanignful information from APARs
features to help in context building
| Context building design | agree on a method to understand text
agree on a method to build context
| Parse Trees | Design Tree
Build Tree
parse tree and extract relationships
| DB structure | Finalize DB structure
Obtain hardware resources to implement DB structure
| Data Pipeline | Define Data pipeline
Create Data Pipeline

## Milestones
Milestones | Delivery Date
Requirements Locked | 2018-05-30
Access to Data Sources | 2018-05-30
Base Taxonomy/Ontology | 2018-06-06
DB structure and Data Flow pipeline | 2018-06-26
Relationship/Entity extraction | 2018-07-14
Ticket processing and search | 2018-08-01
Component Integration | 2018-08-01
Crawler | 2018-08-19
Graph traversal | 2018-09-04
web dashboard | 2018-09-18
querying engine | 2018-10-05
Application Testing | 2018-10-22
UAT | 2018-11-10

## Risks
1 | It is assumed that for all the tasks, off the shelf algorithms and packages are available. In case they are not, the time to code these by ourselves will add a significant amount of time
2 | Planning has been done keeping in mind the number of resources that were promised initially. Delay in the availability of these resources will adversely affect the timelines
3 | external taxonomy/repositries are not of good standard or are not able to add sufficient value to our project forcing us to building these from zero.
4 | Hardware performance issues may arise and we may need to change our hardaware architecture to hadoop/spark